## Sheet1
Strategic objective | Key activites | Type of engagement | Priority | Commissioners/Commission staff | Stakeholder forum | Other stakeholders | Quarter
1 | Amendments to guidance and crafting of clear messages re the implementation of a registration threshold. | User experience | Essential | Policy, Comms and relevant teams | Yes | Helper groups Critical friends | Q.1
1 | Redesign our registration guidance and supporting materials to make them more user friendly. | User experience | Essential | Policy and registration team | Yes | Helper groups and critical friends | Q.1
1 | Increase direct engagement with applicants where they require support to register. | User experience | Essential | Registration team | N/A | Charity trustees Charity contacts and representatives Helper groups | Ongoing
2 | To better understand charity trustees’ existing knowledge of regulatory requirements and what guidance, or tools are required and how we can best support delivery of them. | Listening exercises | Essential | Policy and other teams as required | Yes | Helper groups Charity regulators | Q.2
2 | Raise charity trustee awareness of their statutory responsibilities through the publication of online webinars, vlogs and blogs as requested by stakeholders. | Trustee training | Desirable | Policy, Comms and other teams as required | Yes | Charity trustees, Charity sector, Public | Ongoing
2 | Review and redesign the Commission's website - within budgetary limits. | User experience | Essential | Cororate services, other teams and external experts | Yes | User acceptance testing volunteers external advisers. | Ongoing
2 | Review how guidance is pitched and communicated to charities. | User experience | Essential | Policy, comms and other teams as required | Yes | User feedback from online surveys. Helper groups | Ongoing
2 | Carry out more engagement events, increase roadshows (primarily virtual platforms) and explore other options for using technology to facilitate other methods of engagement. | Events | Essential | Policy, comms and other teams as required | N/A | Partners in the sector: Helper groups | Ongoing
4 | Contributing to working groups to support delivery of the recommendations of the Independent review o cahrity regulation in Northern Ireland. | Working groups | Essential | Cross Commission | Yes | DfC Sector representatives | Ongoing
4 | Building relationships with the charity sector and public. | Variety of means | Essential | Commissioners Commission staff | Yes | Charities Helper groups | Ongoing
4 | Complaint handling: We will deal effectively with complaints by engaging at the earliest opportunity | using a range of methods: telephone, email and online or face to face meetings to improve customer standards. | Essential | Commission staff - all teams primarily Comms, admin, concerns, M&C, casework | N/A | Charity trustees Charity contacts Charity representatives | Ongoing
2 | Quarterly meeting with Fundraising Regulator | Meeting - other regulators | Desirable | Policy | N/A | N/A | Quarterly
2 | Joint event with Fundraising Regulator re changing Code of Fundraising | Events | Essential | Cex | N/A | Sector representatives | Q.2
2 | Events - Presentation at National PTA event | Events | Desirable | Policy | N/A | Charity trustees | Q.1
2 | Meeting with Helper groups - improving engagement | Ongoing engagement | Essential | Policy and others as required | N/A | Helper groups | Q.3
2 | Stakeholder forum meetings | Ongoing engagement | Essential | Policy and others as required | Yes | N/A | Quarterly
2 | Annual public meeting | Open meeting | Essential | Commissioners & SMT | N/A | All stakeholders and the public. | Q. 2
2 | Refresh critical friends’ group | Ongoing engagement | Essential | Policy and others as required | N/A | Sector representatives Professional advisers | Q.3
1 | Feedback from online surveys (Registration and Annual reporting) | User experience | Desirable | Policy | N/A | Charity trustees Charity contacts Professional advisers | Q.2 & Q.4
2 | Review guidance, pitch, tone and how communicated to charities: M&C guidance | Guidance - update | Essential | Monitoring & Compliance, policy and comms | Yes | Helper groups Critical friends | Q.1 & Q.2
1 | Review guidance, pitch, tone and how communicated to charities: Running your charity | Guidance - update | Essential | Policy, Comms and other teams as required | Yes | Critical friends | Q.3
2 | Trustee Governance training - Various groups and trustees | Trustee training | Desirable | Policy and other teams as required | N/A | Charity trustees | Q.2